## Sheet1
VESSEL DECON - Kinder Morgan Galena Park (Barge Docks 1-3)
Resource Identifier |  | Leader |  | Contact Info # |  | # or Persons | Reporting info/Notes/Remarks
Conduct vessel decontamination; wash down oiled areas of the hull using approved methods, remove and dispose of oily waste per plan.
Appropriate PPE should be worn at all times, expect elevated heat conditions during summer months
8 | Yes |  | Water/ Land |  | 6 |  | Harris
Piers/ Wharves, Structures. Kinder Morgan has 05 Ship Docks and 03 Barge Docks. Barge Dock no. 1 - Vessel Type: Barges only, Number of Vsls: (1) one, Max Size: Not specified, Max depth: 14', Mooring Type: Dock/ Dolphin. Dock Description: Not Specified. Barge Dock No. 2 - Barge Only, Max: 02 (two), depth: 14' Mooring: Dock, Description: Limited access. Barge Dock No. 3 - Barge Dock no. 3 - Vessel Type: Barges only, Number of Vsls: (2) two, Max Size: Not specified, Max depth: 14', Mooring Type: Dock/ Dolphin. Dock Description: 12ft height restriction. | [6 empty] | 29 43' 37" N
95 13' 30" W
River Terrace Park |  |  | 10 miles |  |  | workboat
1500 Clinton Drive Galena Park, TX 77547 | [6 empty] | William P. Hobby Airport
Josh Gallien | 281-635-8973
14'
Team to assess and implement booming strategies to protect shoreline and sensitive areas prior to commencing vessel decontamination operations. Recommended to complete double hard boom minimizing boom failure. On site boom with trailer and boat ramp is located at the entrance to ship dock 3.
29. Prepared By: |  |  | 30.Reveiwed by (PSC): |  |  | 31. Reveiwed by (OSC):
"Response strategies may need to be modified to account for changes due to seasonality, weather conditions, spill characteristics, tides and any other pertinent considerations."
1. Incident Name
2. Operational Period (Date/Time)
Assignment List
ICS 204-OS
3. Branch
4. Division/Group
5. Operations Personnel
Operations Section Chief
Branch Director
Division/Group Supervisor
Name
Affiliation
Contact #(s)
6. Resources Assigned This Period
"X" indicates 204a attachment with special instructions
7. Assignments
8. Piers #
9. Onsite Boat Ramp
10. Access
11. On-site Cranes
12. County
14. Latitude
13. Site Information
15. Longitude
16. Closest Public Boat Ramp
17. Land Distance From Ramp
18. Boat Type
20. Closest Airport
21. Closest Helispot
19. Address:
22. Facility Contact Numbers
Atlas Priority:
Environmental:
Economic:
23. Resources at Risk
27. # of Personnel
24. Width of Inlet
25. Water depth
26. Current
28. Booming Strategy Recommendation
Safety Note:
Aerial site Large Scale mapImage
Site Photo #1
Assignment List
ICS 204 OS (DECON Site Plan)
Project Updated:
22. Facility Contact Numbers
14. Latitude
15. Longitude